## CVP
Activity ID | Subject | Hyperscaler | Product Offering | Opportunity Name | Opportunity Number | Opportunity Stage | NAGP ID | NAGP Name | Geo | Geo 1 | CS Manager | CSM | CSE | CS Sales Type | Status | L2C Health Score | Target CS Engagement Start Date | Target CS Engagement Completion Date | Actual CS Engagement Start Date | Actual CS Engagement Completion Date | Fiscal Month | Targeted WL Capacity (TB) | Actual WL Capacity (TB) | TTV | Milestone | Post L2C Destination | Comments | Created Date | Created By | Use Case (1P) | Solution (1P) | WL | Concat | Top 5 | Fiscal Month (Expected to Complete)
00TVV7XBAR3CPDLA | Azure_L2C_Cobalt_Analytics_SMB | Azure | 1P | Cobalt Telecom Ltd-OPP-3980060-Azure-FSxN | 3980060 | Production | NAGP-AZ-003 | Cobalt Telecom Ltd | EMEA-LATAM | EMEA | Sophie Harrington | Chloe Ramsay | Chloe Ramsay | Expansion | Complete | Yellow | 2024-07-01 | 2024-08-17 | 2024-07-04 | 2024-08-28 | 2024M8 | 200 | 200 | 24 | 5) Complete | Partner Led | Synthetic engagement for Cobalt Telecom Ltd on Azure - Complete. | 2024-04-05 | Chloe Ramsay | Analytics | SMB | Analytics | AzureNAGP-AZ-003 | No | 2024M7
00TVVVODFGGFHU12 | AWS_L2C_Atlas_File_Storage_NFSv4 | AWS | 3P | Atlas Capital Partners-OPP-3523964-AWS-FSxN | 3523964 | Closed Won | NAGP-AW-010 | Atlas Capital Partners | EMEA-LATAM | AMER | Ryan Mitchell | Derek Santos | Derek Santos | New Logo | Future | Yellow | 2024-05-25 | 2024-07-09 |  |  | Date not Updated | 300 |  |  | 5) Complete | Existing 1P Named | Synthetic engagement for Atlas Capital Partners on AWS - Future. | 2024-02-07 | Derek Santos | File Storage | NFSv4 | File Storage | AWSNAGP-AW-010 | No | 2024M6
00TVVOND57ZOPLXX | Azure_L2C_Southern_Analytics_Windows SQL | Azure | 3P | Southern Cross Airlines-OPP-7474998-Azure-FSxN | 7474998 | Production | NAGP-AZ-004 | Southern Cross Airlines | Asia Pacific | EMEA | Sophie Harrington | Isabelle Morel | Isabelle Morel | Expansion | Future | Yellow | 2024-06-22 | 2024-08-04 |  |  | Date not Updated | 300 |  |  | 4) Production Go-Live | Partner Led | Synthetic engagement for Southern Cross Airlines on Azure - Future. | 2024-02-11 | Isabelle Morel | Analytics | Windows SQL | Analytics | AzureNAGP-AZ-004 | No | 2024M7
00TVV652T7J5OXVK | GCP_L2C_Lumen_VMware_NFSv3 | GCP | 3P | Lumen Cloud Corp-OPP-5916224-GCP-FSxN | 5916224 | Launch | NAGP-GC-013 | Lumen Cloud Corp | EMEA-LATAM | AMER | Clay Burgess | Sam Cheng | Sam Cheng | Renewal | Started | Yellow | 2024-12-27 | 2025-04-22 | 2024-12-31 |  | Date not Updated | 500 | 109 |  | 5) Complete | Existing 1P Named | Synthetic engagement for Lumen Cloud Corp on GCP - Started. | 2024-03-03 | Sam Cheng | VMware | NFSv3 | VMware | GCPNAGP-GC-013 | No | 2025M3
00TVV05I4MOETALY | AWS_L2C_Harbour_Database_iSCSI | AWS | 1P | Harbour Logistics Corp-OPP-7991279-AWS-ANF | 7991279 | Biz Val | NAGP-AW-008 | Harbour Logistics Corp | Asia Pacific | AMER | Nick Jordan | Sandra Park | Sandra Park | Renewal | Deny | Yellow | 2025-01-31 | 2025-03-23 |  |  | Date not Updated | 600 |  |  | 3) Deployment & Migration | Partner Led | Synthetic engagement for Harbour Logistics Corp on AWS - Deny. | 2024-04-24 | Sandra Park | Database | iSCSI | Database | AWSNAGP-AW-008 | No | 2025M2
00TVV3CBCK8WZUGD | GCP_L2C_Emerald_Database_iSCSI | GCP | 3P | Emerald AI Labs-OPP-2764149-GCP-ANF | 2764149 | Biz Val | NAGP-GC-014 | Emerald AI Labs | North America | EMEA | Lucas Ferreira | Ivan Sokolov | Ivan Sokolov | Expansion | Defer | Green | 2024-08-04 | 2024-10-24 |  |  | Date not Updated | 150 |  |  | 1) Architectural Alignment & Readiness Assessment | Existing 3P CCSM | Synthetic engagement for Emerald AI Labs on GCP - Defer. | 2024-02-17 | Ivan Sokolov | Database | iSCSI | Database | GCPNAGP-GC-014 | No | 2024M9
00TVVJJU6N37R66R | Azure_L2C_Stonegate_Analytics_SMB | Azure | 3P | Stonegate Investment Bank-OPP-7037099-Azure-FSxN | 7037099 | Closed Won | NAGP-AZ-001 | Stonegate Investment Bank | EMEA-LATAM | APAC | James Whitfield | Tom Gallagher | Tom Gallagher | Renewal | Started | Yellow | 2024-04-10 | 2024-05-19 | 2024-04-13 |  | Date not Updated | 200 | 127 |  | 2) Operational Readiness | Partner Led | Synthetic engagement for Stonegate Investment Bank on Azure - Started. | 2024-03-21 | Tom Gallagher | Analytics | SMB | Analytics | AzureNAGP-AZ-001 | No | 2024M4
00TVVWUOFVBBMI1F | Azure_L2C_Fairway_Backup_&_Recovery_iSCSI | Azure | 1P | Fairway Capital Mgmt-OPP-5619651-Azure-ANF | 5619651 | Production | NAGP-AZ-016 | Fairway Capital Mgmt | EMEA-LATAM | EMEA | Sophie Harrington | Dean Forsyth | Dean Forsyth | Renewal | Future | Yellow | 2024-08-26 | 2024-10-02 |  |  | Date not Updated | 400 |  |  | 5) Complete | Existing 3P CCSM | Synthetic engagement for Fairway Capital Mgmt on Azure - Future. | 2024-02-13 | Dean Forsyth | Backup & Recovery | iSCSI | Backup & Recovery | AzureNAGP-AZ-016 | No | 2024M9
00TVVZX3CY03FD1X | GCP_L2C_Brightwave_File_Storage_SMB | GCP | 3P | Brightwave Tech Ltd-OPP-3913196-GCP-FSxN | 3913196 | Production | NAGP-GC-006 | Brightwave Tech Ltd | Asia Pacific | APAC | Tara Simmons | Anaya Roy | Anaya Roy | Expansion | Future | Green | 2024-04-09 | 2024-06-23 |  |  | Date not Updated | 200 |  |  | 2) Operational Readiness | New Logo | Synthetic engagement for Brightwave Tech Ltd on GCP - Future. | 2024-04-02 | Anaya Roy | File Storage | SMB | File Storage | GCPNAGP-GC-006 | No | 2024M5
00TVVXS7I7229U0V | GCP_L2C_Helix_File_Storage_NFSv4 | GCP | 1P | Helix Streaming Ltd-OPP-9330851-GCP-FSxN | 9330851 | Launch | NAGP-GC-003 | Helix Streaming Ltd | North America | EMEA | Lucas Ferreira | Eva Richter | Eva Richter | New Logo | Complete | Green | 2024-02-25 | 2024-04-15 | 2024-02-22 | 2024-05-11 | 2024M4 | 500 | 500 | 105 | 5) Complete | Partner Led | Synthetic engagement for Helix Streaming Ltd on GCP - Complete. | 2024-02-16 | Eva Richter | File Storage | NFSv4 | File Storage | GCPNAGP-GC-003 | No | 2024M3
00TVVKR2BFY4X28N | AWS_L2C_Vertex_Database_NFSv3 | AWS | 1P | Vertex Insurance Holdings-OPP-5961558-AWS-FSxN | 5961558 | Production | NAGP-AW-004 | Vertex Insurance Holdings | North America | AMER | Ryan Mitchell | Aaron Blake | Aaron Blake | New Logo | Future | Red | 2024-06-01 | 2024-09-17 |  |  | Date not Updated | 200 |  |  | 3) Deployment & Migration | Existing 1P Named | Synthetic engagement for Vertex Insurance Holdings on AWS - Future. | 2024-03-25 | Aaron Blake | Database | NFSv3 | Database | AWSNAGP-AW-004 | No | 2024M8
00TVVS9HXFUPUBH6 | Azure_L2C_Midlands_Backup_&_Recovery_iSCSI | Azure | 3P | Midlands Energy Corp-OPP-3921829-Azure-ANF | 3921829 | Biz Val | NAGP-AZ-012 | Midlands Energy Corp | EMEA-LATAM | AMER | Brett Calloway | Fiona Clements | Fiona Clements | Renewal | Started | Green | 2024-04-16 | 2024-08-04 | 2024-04-15 |  | Date not Updated | 50 | 26 |  | 2) Operational Readiness | Existing 1P Named | Synthetic engagement for Midlands Energy Corp on Azure - Started. | 2024-02-07 | Fiona Clements | Backup & Recovery | iSCSI | Backup & Recovery | AzureNAGP-AZ-012 | No | 2024M7
00TVVME7DSIUH4PH | AWS_L2C_Pinnacle_File_Storage_NFSv4 | AWS | 3P | Pinnacle Financial Corp-OPP-4914399-AWS-FSxN | 4914399 | Production | NAGP-AW-001 | Pinnacle Financial Corp | North America | AMER | Chris Dolan | Owen Griffith | Owen Griffith | Renewal | Future | Red | 2024-04-12 | 2024-05-29 |  |  | Date not Updated | 500 |  |  | 5) Complete | New Logo | Synthetic engagement for Pinnacle Financial Corp on AWS - Future. | 2024-04-18 | Owen Griffith | File Storage | NFSv4 | File Storage | AWSNAGP-AW-001 | No | 2024M5
00TVVYPSCJ1MG2BB | GCP_L2C_SouthBank_Database_NFSv4 | GCP | 1P | SouthBank Fintech-OPP-4804654-GCP-FSxN | 4804654 | Launch | NAGP-GC-010 | SouthBank Fintech | EMEA-LATAM | AMER | Clay Burgess | Jake Morrison | Jake Morrison | Renewal | Deny | Yellow | 2024-02-15 | 2024-04-25 |  |  | Date not Updated | 200 |  |  | 5) Complete | New Logo | Synthetic engagement for SouthBank Fintech on GCP - Deny. | 2024-01-21 | Jake Morrison | Database | NFSv4 | Database | GCPNAGP-GC-010 | No | 2024M3
00TVVFOZTHC8MFC5 | Azure_L2C_Celestia_Database_iSCSI | Azure | 3P | Celestia Biotech-OPP-2913881-Azure-ANF | 2913881 | Production | NAGP-AZ-014 | Celestia Biotech | North America | EMEA | Sophie Harrington | Isabelle Morel | Isabelle Morel | New Logo | Defer | Green | 2024-01-24 | 2024-04-08 |  |  | Date not Updated | 300 |  |  | 3) Deployment & Migration | Existing 1P Named | Synthetic engagement for Celestia Biotech on Azure - Defer. | 2024-03-03 | Isabelle Morel | Database | iSCSI | Database | AzureNAGP-AZ-014 | No | 2024M3
00TVV1CAEPY9NP51 | AWS_L2C_Meridian_Database_Windows SQL | AWS | 1P | Meridian Healthcare Ltd-OPP-5293614-AWS-FSxN | 5293614 | Production | NAGP-AW-002 | Meridian Healthcare Ltd | North America | AMER | Ryan Mitchell | Aaron Blake | Aaron Blake | Renewal | Complete | Green | 2024-12-10 | 2025-02-11 | 2024-12-10 | 2025-02-23 | 2025M1 | 300 | 300 | 39 | 5) Complete | Existing 3P CCSM | Synthetic engagement for Meridian Healthcare Ltd on AWS - Complete. | 2024-02-18 | Aaron Blake | Database | Windows SQL | Database | AWSNAGP-AW-002 | No | 2025M1
00TVVHXSVJ1EAR73 | GCP_L2C_Nimbus_VMware_Windows SQL | GCP | 1P | Nimbus Analytics Corp-OPP-5078610-GCP-FSxN | 5078610 | Production | NAGP-GC-002 | Nimbus Analytics Corp | EMEA-LATAM | APAC | Tara Simmons | Anaya Roy | Anaya Roy | New Logo | Future | Red | 2024-08-28 | 2024-11-20 |  |  | Date not Updated | 300 |  |  | 5) Complete | Existing 1P Named | Synthetic engagement for Nimbus Analytics Corp on GCP - Future. | 2024-03-20 | Anaya Roy | VMware | Windows SQL | VMware | GCPNAGP-GC-002 | No | 2024M10
00TVV0MVZBDEOPXV | Azure_L2C_Golden_File_Storage_SMB | Azure | 1P | Golden Gate Retail-OPP-8613012-Azure-FSxN | 8613012 | Production | NAGP-AZ-006 | Golden Gate Retail | Asia Pacific | AMER | Brett Calloway | Fiona Clements | Fiona Clements | Renewal | Future | Red | 2024-01-24 | 2024-02-25 |  |  | Date not Updated | 100 |  |  | 3) Deployment & Migration | Existing 1P Named | Synthetic engagement for Golden Gate Retail on Azure - Future. | 2024-02-25 | Fiona Clements | File Storage | SMB | File Storage | AzureNAGP-AZ-006 | No | 2024M1
00TVVZD41NDJSJ9F | GCP_L2C_Tidal_Database_NFSv4 | GCP | 3P | Tidal Data Systems-OPP-3973552-GCP-FSxN | 3973552 | Biz Val | NAGP-GC-011 | Tidal Data Systems | North America | AMER | Clay Burgess | Rachel Torres | Rachel Torres | Renewal | Started | Yellow | 2024-06-03 | 2024-07-18 | 2024-05-29 |  | Date not Updated | 100 | 42 |  | 3) Deployment & Migration | Partner Led | Synthetic engagement for Tidal Data Systems on GCP - Started. | 2024-03-15 | Rachel Torres | Database | NFSv4 | Database | GCPNAGP-GC-011 | No | 2024M6
00TVVWQFLESWVCU2 | GCP_L2C_Alpine_Analytics_Windows SQL | GCP | 3P | Alpine Data Ventures-OPP-5243953-GCP-FSxN | 5243953 | Closed Won | NAGP-GC-017 | Alpine Data Ventures | EMEA-LATAM | APAC | Tara Simmons | Kenji Watanabe | Kenji Watanabe | Expansion | Started | Green | 2024-11-03 | 2024-12-03 | 2024-11-03 |  | Date not Updated | 400 | 307 |  | 5) Complete | Partner Led | Synthetic engagement for Alpine Data Ventures on GCP - Started. | 2024-01-25 | Kenji Watanabe | Analytics | Windows SQL | Analytics | GCPNAGP-GC-017 | No | 2024M11
00TVVKE0ZGTXDEA4 | GCP_L2C_Polar_Database_NFSv3 | GCP | 1P | Polar Fashion Group-OPP-5055025-GCP-FSxN | 5055025 | Launch | NAGP-GC-008 | Polar Fashion Group | EMEA-LATAM | EMEA | Lucas Ferreira | Ivan Sokolov | Ivan Sokolov | Expansion | Complete | Red | 2024-06-15 | 2024-09-04 | 2024-06-15 | 2024-08-16 | 2024M7 | 50 | 50 | 123 | 5) Complete | New Logo | Synthetic engagement for Polar Fashion Group on GCP - Complete. | 2024-04-07 | Ivan Sokolov | Database | NFSv3 | Database | GCPNAGP-GC-008 | No | 2024M8
00TVV43WVZ8VU04T | AWS_L2C_Orion_VMware_iSCSI | AWS | 1P | Orion Retail Group-OPP-4884674-AWS-ANF | 4884674 | Production | NAGP-AW-003 | Orion Retail Group | North America | AMER | Nick Jordan | Priya Kapoor | Priya Kapoor | Expansion | Future | Green | 2024-01-25 | 2024-02-26 |  |  | Date not Updated | 300 |  |  | 5) Complete | Existing 1P Named | Synthetic engagement for Orion Retail Group on AWS - Future. | 2024-02-03 | Priya Kapoor | VMware | iSCSI | VMware | AWSNAGP-AW-003 | No | 2024M2
00TVVY1DTB6PWBWR | AWS_L2C_Ironbridge_VMware_NFSv4 | AWS | 3P | Ironbridge Manufacturing-OPP-6518103-AWS-FSxN | 6518103 | Launch | NAGP-AW-011 | Ironbridge Manufacturing | North America | AMER | Chris Dolan | Owen Griffith | Owen Griffith | New Logo | Future | Red | 2024-08-21 | 2024-11-28 |  |  | Date not Updated | 600 |  |  | 5) Complete | Partner Led | Synthetic engagement for Ironbridge Manufacturing on AWS - Future. | 2024-03-03 | Owen Griffith | VMware | NFSv4 | VMware | AWSNAGP-AW-011 | No | 2024M11
00TVVJDAOVVV99J6 | Azure_L2C_Emerald_VMware_NFSv4 | Azure | 1P | Emerald Property Group-OPP-2058890-Azure-FSxN | 2058890 | Launch | NAGP-AZ-002 | Emerald Property Group | EMEA-LATAM | AMER | Brett Calloway | Fiona Clements | Fiona Clements | Renewal | Complete | Green | 2024-03-24 | 2024-07-17 | 2024-03-21 | 2024-05-08 | 2024M4 | 50 | 50 | 150 | 5) Complete | Partner Led | Synthetic engagement for Emerald Property Group on Azure - Complete. | 2024-03-20 | Fiona Clements | VMware | NFSv4 | VMware | AzureNAGP-AZ-002 | No | 2024M6
00TVV4M6IXRK29E3 | GCP_L2C_Vantage_VMware_Datastore (for GCVE, VMC, AVS) | GCP | 3P | Vantage Commerce Inc-OPP-2551390-GCP-ANF | 2551390 | Launch | NAGP-GC-004 | Vantage Commerce Inc | North America | EMEA | Lucas Ferreira | Camille Dupont | Camille Dupont | New Logo | Defer | Red | 2024-02-19 | 2024-05-04 |  |  | Date not Updated | 600 |  |  | 4) Production Go-Live | Existing 1P Named | Synthetic engagement for Vantage Commerce Inc on GCP - Defer. | 2024-01-31 | Camille Dupont | VMware | Datastore (for GCVE, VMC, AVS) | VMware | GCPNAGP-GC-004 | No | 2024M4
00TVVX1RZHBH9P58 | Azure_L2C_Horizon_File_Storage_Datastore (for GCVE, VMC, AVS) | Azure | 1P | Horizon Auto Group-OPP-4397932-Azure-ANF | 4397932 | Closed Won | NAGP-AZ-013 | Horizon Auto Group | North America | EMEA | Sophie Harrington | Dean Forsyth | Dean Forsyth | New Logo | Complete | Green | 2024-10-22 | 2025-01-18 | 2024-10-21 | 2025-01-12 | 2024M12 | 50 | 50 | 18 | 5) Complete | Existing 3P CCSM | Synthetic engagement for Horizon Auto Group on Azure - Complete. | 2024-02-22 | Dean Forsyth | File Storage | Datastore (for GCVE, VMC, AVS) | File Storage | AzureNAGP-AZ-013 | No | 2024M12
00TVVZF72UN4X8JS | GCP_L2C_Ironveil_Database_Windows SQL | GCP | 3P | Ironveil Cybersecurity-OPP-6848838-GCP-FSxN | 6848838 | Launch | NAGP-GC-012 | Ironveil Cybersecurity | North America | EMEA | Lucas Ferreira | Eva Richter | Eva Richter | Expansion | Started | Green | 2024-09-16 | 2024-10-26 | 2024-09-17 |  | Date not Updated | 400 | 378 |  | 5) Complete | Existing 3P CCSM | Synthetic engagement for Ironveil Cybersecurity on GCP - Started. | 2024-02-17 | Eva Richter | Database | Windows SQL | Database | GCPNAGP-GC-012 | No | 2024M9
00TVVTIJOO5NFFQJ | AWS_L2C_Crestline_Database_iSCSI | AWS | 1P | Crestline Energy Inc-OPP-3674647-AWS-ANF | 3674647 | Production | NAGP-AW-005 | Crestline Energy Inc | North America | AMER | Ryan Mitchell | Aaron Blake | Aaron Blake | New Logo | Started | Red | 2024-09-17 | 2025-01-05 | 2024-09-17 |  | Date not Updated | 150 | 93 |  | 1) Architectural Alignment & Readiness Assessment | Existing 1P Named | Synthetic engagement for Crestline Energy Inc on AWS - Started. | 2024-03-27 | Aaron Blake | Database | iSCSI | Database | AWSNAGP-AW-005 | No | 2024M12
00TVV2OLPL9ZD912 | AWS_L2C_Pacific_Analytics_NFSv4 | AWS | 1P | Pacific Wealth Management-OPP-2974935-AWS-FSxN | 2974935 | Biz Val | NAGP-AW-007 | Pacific Wealth Management | Asia Pacific | AMER | Chris Dolan | Owen Griffith | Owen Griffith | Renewal | Future | Yellow | 2024-07-30 | 2024-09-18 |  |  | Date not Updated | 200 |  |  | 5) Complete | Existing 1P Named | Synthetic engagement for Pacific Wealth Management on AWS - Future. | 2024-04-15 | Owen Griffith | Analytics | NFSv4 | Analytics | AWSNAGP-AW-007 | No | 2024M8
00TVVN0JMAGUWVXL | Azure_L2C_Pacifica_File_Storage_iSCSI | Azure | 1P | Pacifica Utilities Corp-OPP-8897422-Azure-ANF | 8897422 | Launch | NAGP-AZ-005 | Pacifica Utilities Corp | Asia Pacific | EMEA | Sophie Harrington | Chloe Ramsay | Chloe Ramsay | New Logo | Complete | Green | 2025-01-26 | 2025-03-18 | 2025-01-30 | 2025-04-29 | 2025M4 | 150 | 150 | 133 | 5) Complete | Partner Led | Synthetic engagement for Pacifica Utilities Corp on Azure - Complete. | 2024-03-27 | Chloe Ramsay | File Storage | iSCSI | File Storage | AzureNAGP-AZ-005 | No | 2025M2
00TVVTW2R86QERN5 | Azure_L2C_Ridgeway_Backup_&_Recovery_Datastore (for GCVE, VMC, AVS) | Azure | 3P | Ridgeway Pharma Group-OPP-6032258-Azure-ANF | 6032258 | Closed Won | NAGP-AZ-011 | Ridgeway Pharma Group | EMEA-LATAM | APAC | James Whitfield | Tom Gallagher | Tom Gallagher | New Logo | Defer | Yellow | 2024-06-23 | 2024-07-30 |  |  | Date not Updated | 200 |  |  | 5) Complete | Existing 1P Named | Synthetic engagement for Ridgeway Pharma Group on Azure - Defer. | 2024-01-31 | Tom Gallagher | Backup & Recovery | Datastore (for GCVE, VMC, AVS) | Backup & Recovery | AzureNAGP-AZ-011 | No | 2024M7
00TVVAZCBHG79H1G | GCP_L2C_Cosmo_Database_NFSv4 | GCP | 1P | Cosmo Ride Platforms-OPP-5258814-GCP-FSxN | 5258814 | Production | NAGP-GC-007 | Cosmo Ride Platforms | Asia Pacific | AMER | Clay Burgess | Sam Cheng | Sam Cheng | Expansion | Complete | Green | 2024-05-29 | 2024-08-27 | 2024-05-29 | 2024-08-20 | 2024M7 | 300 | 300 | 98 | 5) Complete | Partner Led | Synthetic engagement for Cosmo Ride Platforms on GCP - Complete. | 2024-02-27 | Sam Cheng | Database | NFSv4 | Database | GCPNAGP-GC-007 | No | 2024M8
00TVV14MZQX2RRQJ | Azure_L2C_NovaTech_Database_Datastore (for GCVE, VMC, AVS) | Azure | 1P | NovaTech Platforms Inc-OPP-5737276-Azure-ANF | 5737276 | Launch | NAGP-AZ-007 | NovaTech Platforms Inc | North America | EMEA | Sophie Harrington | Dean Forsyth | Dean Forsyth | New Logo | Complete | Red | 2024-11-19 | 2024-12-30 | 2024-11-19 | 2024-12-25 | 2024M12 | 50 | 50 | 118 | 5) Complete | Existing 1P Named | Synthetic engagement for NovaTech Platforms Inc on Azure - Complete. | 2024-04-15 | Dean Forsyth | Database | Datastore (for GCVE, VMC, AVS) | Database | AzureNAGP-AZ-007 | No | 2024M12
00TVV767JG3X48CY | AWS_L2C_Redwood_Backup_&_Recovery_Windows SQL | AWS | 3P | Redwood Genomics-OPP-6367130-AWS-FSxN | 6367130 | Launch | NAGP-AW-014 | Redwood Genomics | North America | AMER | Ryan Mitchell | Derek Santos | Derek Santos | Expansion | Future | Yellow | 2024-02-20 | 2024-03-31 |  |  | Date not Updated | 200 |  |  | 3) Deployment & Migration | Existing 3P CCSM | Synthetic engagement for Redwood Genomics on AWS - Future. | 2024-01-29 | Derek Santos | Backup & Recovery | Windows SQL | Backup & Recovery | AWSNAGP-AW-014 | No | 2024M3
00TVVGX5LNR2GZ2Y | Azure_L2C_Silverline_Backup_&_Recovery_Windows SQL | Azure | 1P | Silverline Media Corp-OPP-7653926-Azure-FSxN | 7653926 | Production | NAGP-AZ-010 | Silverline Media Corp | EMEA-LATAM | AMER | Brett Calloway | Nathan Kowalski | Nathan Kowalski | Renewal | Complete | Green | 2024-12-16 | 2025-01-22 | 2024-12-13 | 2025-01-14 | 2024M12 | 250 | 250 | 100 | 5) Complete | New Logo | Synthetic engagement for Silverline Media Corp on Azure - Complete. | 2024-03-15 | Nathan Kowalski | Backup & Recovery | Windows SQL | Backup & Recovery | AzureNAGP-AZ-010 | No | 2024M12
00TVVJ73DUAVGRM9 | GCP_L2C_Dawnridge_VMware_NFSv4 | GCP | 1P | Dawnridge IoT-OPP-5167161-GCP-FSxN | 5167161 | Biz Val | NAGP-GC-015 | Dawnridge IoT | Asia Pacific | APAC | Tara Simmons | Liam O'Brien | Liam O'Brien | Expansion | Defer | Yellow | 2025-02-15 | 2025-04-15 |  |  | Date not Updated | 200 |  |  | 1) Architectural Alignment & Readiness Assessment | Existing 3P CCSM | Synthetic engagement for Dawnridge IoT on GCP - Defer. | 2024-03-09 | Liam O'Brien | VMware | NFSv4 | VMware | GCPNAGP-GC-015 | No | 2025M3
00TVV82HTZG9J4AD | Azure_L2C_Stonewall_Backup_&_Recovery_NFSv3 | Azure | 3P | Stonewall Logistics-OPP-6704072-Azure-FSxN | 6704072 | Closed Won | NAGP-AZ-015 | Stonewall Logistics | Asia Pacific | APAC | James Whitfield | Tom Gallagher | Tom Gallagher | Renewal | Started | Red | 2024-01-23 | 2024-03-24 | 2024-01-19 |  | Date not Updated | 100 | 19 |  | 2) Operational Readiness | New Logo | Synthetic engagement for Stonewall Logistics on Azure - Started. | 2024-01-23 | Tom Gallagher | Backup & Recovery | NFSv3 | Backup & Recovery | AzureNAGP-AZ-015 | No | 2024M2
00TVVPQSLCGL3VWY | GCP_L2C_Apex_Analytics_Datastore (for GCVE, VMC, AVS) | GCP | 1P | Apex Delivery Networks-OPP-1786967-GCP-ANF | 1786967 | Biz Val | NAGP-GC-009 | Apex Delivery Networks | EMEA-LATAM | APAC | Tara Simmons | Liam O'Brien | Liam O'Brien | Renewal | Started | Yellow | 2024-02-06 | 2024-05-11 | 2024-02-09 |  | Date not Updated | 300 | 130 |  | 5) Complete | Partner Led | Synthetic engagement for Apex Delivery Networks on GCP - Started. | 2024-04-02 | Liam O'Brien | Analytics | Datastore (for GCVE, VMC, AVS) | Analytics | GCPNAGP-GC-009 | No | 2024M4
00TVVHGPC64CI31T | GCP_L2C_Stratus_Analytics_NFSv3 | GCP | 1P | Stratus Digital Media-OPP-4065342-GCP-FSxN | 4065342 | Launch | NAGP-GC-001 | Stratus Digital Media | North America | APAC | Tara Simmons | Kenji Watanabe | Kenji Watanabe | New Logo | Complete | Yellow | 2024-12-26 | 2025-04-13 | 2024-12-28 | 2025-03-11 | 2025M2 | 500 | 500 | 79 | 5) Complete | Existing 3P CCSM | Synthetic engagement for Stratus Digital Media on GCP - Complete. | 2024-04-19 | Kenji Watanabe | Analytics | NFSv3 | Analytics | GCPNAGP-GC-001 | No | 2025M3
00TVV2VDE5XGI5EV | Azure_L2C_Copperton_Backup_&_Recovery_Windows SQL | Azure | 3P | Copperton Supplies Ltd-OPP-5112276-Azure-FSxN | 5112276 | Production | NAGP-AZ-017 | Copperton Supplies Ltd | Asia Pacific | APAC | James Whitfield | Anya Petrov | Anya Petrov | New Logo | Started | Yellow | 2025-02-07 | 2025-06-01 | 2025-02-06 |  | Date not Updated | 50 | 28 |  | 4) Production Go-Live | Existing 1P Named | Synthetic engagement for Copperton Supplies Ltd on Azure - Started. | 2024-03-04 | Anya Petrov | Backup & Recovery | Windows SQL | Backup & Recovery | AzureNAGP-AZ-017 | No | 2025M5
00TVVM48MYHKHSD3 | GCP_L2C_Vortex_VMware_NFSv4 | GCP | 3P | Vortex Mobility Inc-OPP-9092293-GCP-FSxN | 9092293 | Launch | NAGP-GC-016 | Vortex Mobility Inc | Asia Pacific | AMER | Clay Burgess | Sam Cheng | Sam Cheng | New Logo | Deny | Yellow | 2025-01-06 | 2025-04-19 |  |  | Date not Updated | 150 |  |  | 2) Operational Readiness | Partner Led | Synthetic engagement for Vortex Mobility Inc on GCP - Deny. | 2024-03-15 | Sam Cheng | VMware | NFSv4 | VMware | GCPNAGP-GC-016 | No | 2025M3
00TVVK4A71WJDOSU | AWS_L2C_Quantum_File_Storage_SMB | AWS | 3P | Quantum Data Systems-OPP-8705379-AWS-FSxN | 8705379 | Closed Won | NAGP-AW-017 | Quantum Data Systems | North America | AMER | Ryan Mitchell | Derek Santos | Derek Santos | Expansion | Complete | Green | 2024-04-17 | 2024-07-24 | 2024-04-17 | 2024-05-29 | 2024M5 | 150 | 150 | 16 | 5) Complete | Partner Led | Synthetic engagement for Quantum Data Systems on AWS - Complete. | 2024-03-20 | Derek Santos | File Storage | SMB | File Storage | AWSNAGP-AW-017 | No | 2024M6
00TVVWQ4VILYA820 | AWS_L2C_BlueStar_Backup_&_Recovery_SMB | AWS | 3P | BlueStar Banking Grp-OPP-1049445-AWS-FSxN | 1049445 | Biz Val | NAGP-AW-006 | BlueStar Banking Grp | Asia Pacific | AMER | Nick Jordan | Tyler Reeves | Tyler Reeves | Renewal | Deny | Yellow | 2025-01-10 | 2025-03-17 |  |  | Date not Updated | 200 |  |  | 4) Production Go-Live | Existing 3P CCSM | Synthetic engagement for BlueStar Banking Grp on AWS - Deny. | 2024-02-13 | Tyler Reeves | Backup & Recovery | SMB | Backup & Recovery | AWSNAGP-AW-006 | No | 2025M2
00TVVHDNTYFU63DC | AWS_L2C_Solaris_VMware_iSCSI | AWS | 3P | Solaris Tech Solutions-OPP-3960567-AWS-ANF | 3960567 | Closed Won | NAGP-AW-009 | Solaris Tech Solutions | EMEA-LATAM | AMER | Chris Dolan | Marcus Webb | Marcus Webb | Expansion | Started | Green | 2024-07-02 | 2024-10-02 | 2024-06-29 |  | Date not Updated | 200 | 139 |  | 1) Architectural Alignment & Readiness Assessment | New Logo | Synthetic engagement for Solaris Tech Solutions on AWS - Started. | 2024-01-24 | Marcus Webb | VMware | iSCSI | VMware | AWSNAGP-AW-009 | No | 2024M9
00TVV0Q0FQJNNCSH | AWS_L2C_TerraFin_Backup_&_Recovery_Datastore (for GCVE, VMC, AVS) | AWS | 3P | TerraFin Services-OPP-6472038-AWS-ANF | 6472038 | Closed Won | NAGP-AW-016 | TerraFin Services | EMEA-LATAM | AMER | Chris Dolan | Jessica Lane | Jessica Lane | New Logo | Complete | Green | 2024-10-07 | 2025-01-31 | 2024-10-10 | 2024-11-10 | 2024M10 | 500 | 500 | 119 | 5) Complete | Existing 1P Named | Synthetic engagement for TerraFin Services on AWS - Complete. | 2024-03-23 | Jessica Lane | Backup & Recovery | Datastore (for GCVE, VMC, AVS) | Backup & Recovery | AWSNAGP-AW-016 | No | 2025M1
00TVVCTNFIN40MC1 | AWS_L2C_SkyRoute_Analytics_NFSv3 | AWS | 3P | SkyRoute Airlines-OPP-4774827-AWS-FSxN | 4774827 | Production | NAGP-AW-015 | SkyRoute Airlines | Asia Pacific | AMER | Chris Dolan | Jessica Lane | Jessica Lane | Expansion | Defer | Red | 2024-12-04 | 2025-03-05 |  |  | Date not Updated | 50 |  |  | 2) Operational Readiness | Partner Led | Synthetic engagement for SkyRoute Airlines on AWS - Defer. | 2024-04-20 | Jessica Lane | Analytics | NFSv3 | Analytics | AWSNAGP-AW-015 | No | 2025M2
00TVVJERQWO207B3 | AWS_L2C_Cascade_Backup_&_Recovery_Windows SQL | AWS | 3P | Cascade Media Networks-OPP-4270647-AWS-FSxN | 4270647 | Biz Val | NAGP-AW-012 | Cascade Media Networks | North America | AMER | Ryan Mitchell | Derek Santos | Derek Santos | Renewal | Complete | Red | 2024-11-08 | 2025-02-11 | 2024-11-03 | 2025-01-05 | 2024M12 | 300 | 300 | 138 | 5) Complete | Existing 1P Named | Synthetic engagement for Cascade Media Networks on AWS - Complete. | 2024-02-21 | Derek Santos | Backup & Recovery | Windows SQL | Backup & Recovery | AWSNAGP-AW-012 | No | 2025M1
00TVVGJRU0BVDTHZ | GCP_L2C_Sunridge_Analytics_Windows SQL | GCP | 3P | Sunridge Gaming Corp-OPP-1612079-GCP-FSxN | 1612079 | Production | NAGP-GC-005 | Sunridge Gaming Corp | Asia Pacific | EMEA | Lucas Ferreira | Ivan Sokolov | Ivan Sokolov | Renewal | Complete | Red | 2024-09-14 | 2024-11-25 | 2024-09-10 | 2024-11-09 | 2024M10 | 600 | 600 | 38 | 5) Complete | Existing 3P CCSM | Synthetic engagement for Sunridge Gaming Corp on GCP - Complete. | 2024-03-12 | Ivan Sokolov | Analytics | Windows SQL | Analytics | GCPNAGP-GC-005 | No | 2024M11
00TVVXAKQHP4LS67 | AWS_L2C_Northgate_VMware_iSCSI | AWS | 1P | Northgate Pharma-OPP-3288510-AWS-ANF | 3288510 | Closed Won | NAGP-AW-013 | Northgate Pharma | EMEA-LATAM | AMER | Chris Dolan | Marcus Webb | Marcus Webb | New Logo | Complete | Green | 2024-02-10 | 2024-06-05 | 2024-02-10 | 2024-03-25 | 2024M3 | 150 | 150 | 91 | 5) Complete | Partner Led | Synthetic engagement for Northgate Pharma on AWS - Complete. | 2024-01-16 | Marcus Webb | VMware | iSCSI | VMware | AWSNAGP-AW-013 | No | 2024M5
00TVV51CUF613TOL | Azure_L2C_Lakeside_Analytics_iSCSI | Azure | 3P | Lakeside Financial Grp-OPP-7227171-Azure-ANF | 7227171 | Closed Won | NAGP-AZ-008 | Lakeside Financial Grp | North America | APAC | James Whitfield | Anya Petrov | Anya Petrov | Expansion | Complete | Green | 2024-06-11 | 2024-08-12 | 2024-06-08 | 2024-08-23 | 2024M7 | 100 | 100 | 72 | 5) Complete | Existing 1P Named | Synthetic engagement for Lakeside Financial Grp on Azure - Complete. | 2024-04-08 | Anya Petrov | Analytics | iSCSI | Analytics | AzureNAGP-AZ-008 | No | 2024M7

## FISCAL CALENDAR
Fiscal Month | Start Date | End Date
2024M1 | 2024-01-29 | 2024-02-25
2024M2 | 2024-02-26 | 2024-03-24
2024M3 | 2024-03-25 | 2024-04-28
2024M4 | 2024-04-29 | 2024-05-26
2024M5 | 2024-05-27 | 2024-06-23
2024M6 | 2024-06-24 | 2024-07-28
2024M7 | 2024-07-29 | 2024-08-25
2024M8 | 2024-08-26 | 2024-09-22
2024M9 | 2024-09-23 | 2024-10-27
2024M10 | 2024-10-28 | 2024-11-24
2024M11 | 2024-11-25 | 2024-12-22
2024M12 | 2024-12-23 | 2025-01-26
2025M1 | 2025-01-27 | 2025-02-23
2025M2 | 2025-02-24 | 2025-03-23
2025M3 | 2025-03-24 | 2025-04-27
2025M4 | 2025-04-28 | 2025-05-25
2025M5 | 2025-05-26 | 2025-06-22
2025M6 | 2025-06-23 | 2025-07-27
2025M7 | 2025-07-28 | 2025-08-24
2025M8 | 2025-08-25 | 2025-09-21
2025M9 | 2025-09-22 | 2025-10-26
2025M10 | 2025-10-27 | 2025-11-23
2025M11 | 2025-11-24 | 2025-12-21
2025M12 | 2025-12-22 | 2026-01-25
2026M1 | 2026-01-26 | 2026-02-22
2026M2 | 2026-02-23 | 2026-03-22
2026M3 | 2026-03-23 | 2026-04-26
2026M4 | 2026-04-27 | 2026-05-24
2026M5 | 2026-05-25 | 2026-06-21
2026M6 | 2026-06-22 | 2026-07-26
2026M7 | 2026-07-27 | 2026-08-23
2026M8 | 2026-08-24 | 2026-09-20
2026M9 | 2026-09-21 | 2026-10-25
2026M10 | 2026-10-26 | 2026-11-22
2026M11 | 2026-11-23 | 2026-12-20
2026M12 | 2026-12-21 | 2027-01-24
2027M1 | 2027-01-25 | 2027-02-28
2027M2 | 2027-03-01 | 2027-04-04
2027M3 | 2027-04-05 | 2027-05-09
2027M4 | 2027-05-10 | 2027-06-06
2027M5 | 2027-06-07 | 2027-07-04
2027M6 | 2027-07-05 | 2027-08-08
2027M7 | 2027-08-09 | 2027-09-05
2027M8 | 2027-09-06 | 2027-10-03
2027M9 | 2027-10-04 | 2027-11-07
2027M10 | 2027-11-08 | 2027-12-05
2027M11 | 2027-12-06 | 2028-01-02
2027M12 | 2028-01-03 | 2028-02-06

## 1P
NAGP ID | NAGP Name | Geo | Account Name | Strategic Programs | Opportunity Owner | Opportunity Owner: Manager | Opportunity Name | Copy Opportunity | Created Date | Close Date | New Logo | New Workload | Stage | Use Case (1P) | Solution (1P) | Product Name | Expected Capacity in Terabytes | Ex Capacity Bucket | Days in Sales Stage | Opportunity Age | POC Status | Last Modified Date | Next Step | Blocker Details | Blocker Notes | Revenue (converted) Currency | Revenue (converted) | Hyperscaler | Opportunity Number | L2C Status | Comments | Oppty Unique Count | Concat | Top 5
NAGP-AW-012 | Cascade Media Networks | North America | Cascade Media Networks | Searchlight | Tyler Reeves | Nick Jordan | Cascade Media Networks-AWS-FSxN-Analytics | 0 | 2024-06-13 | 2024-12-04 | 1 | 1 | Closed Won | Analytics | NFSv3 | FSxN | 750 | High | 471 | 182 | In Progress | 2025-01-22 | Follow up with Cascade Media Networks on Analytics deployment. |  |  | USD | 101357.31 | AWS | 1014545 | Future | CVP Created | 1 | AWSNAGP-AW-012 | No
NAGP-GC-014 | Emerald AI Labs | North America | Emerald AI Labs | Lighthouse | Liam O'Brien | Tara Simmons | Emerald AI Labs-GCP-FSxN-Backup_&_Recovery | 0 | 2024-03-13 | 2025-06-18 | 0 | 1 | Closed Won | Backup & Recovery | NFSv4 | FSxN | 450 | High | 499 | 491 |  | 2024-10-29 | Follow up with Emerald AI Labs on Backup & Recovery deployment. | Security review |  | USD | 214499.46 | GCP | 4047277 | Started | CVP Created | 1 | GCPNAGP-GC-014 | No
NAGP-AW-010 | Atlas Capital Partners | EMEA-LATAM | Atlas Capital Partners | Keystone | Priya Kapoor | Nick Jordan | Atlas Capital Partners-AWS-FSxN-Backup_&_Recovery | 0 | 2024-03-18 | 2025-09-03 | 0 | 0 | Closed Won | Backup & Recovery | NFSv4 | FSxN | 450 | High | 48 | 673 | In Progress | 2024-12-20 | Follow up with Atlas Capital Partners on Backup & Recovery deployment. | Budget freeze |  | USD | 58766.62 | AWS | 8050897 | Started | CVP Created | 1 | AWSNAGP-AW-010 | No
NAGP-AW-015 | SkyRoute Airlines | Asia Pacific | SkyRoute Airlines | Keystone | Owen Griffith | Chris Dolan | SkyRoute Airlines-AWS-FSxN-Backup_&_Recovery | 0 | 2024-04-13 | 2025-06-24 | 1 | 0 | Biz Val | Backup & Recovery | NFSv3 | FSxN | 750 | High | 167 | 442 |  | 2025-05-26 | Follow up with SkyRoute Airlines on Backup & Recovery deployment. | Security review |  | USD | 107847.3 | AWS | 5191215 | Complete | CVP Created | 1 | AWSNAGP-AW-015 | No
NAGP-GC-006 | Brightwave Tech Ltd | Asia Pacific | Brightwave Tech Ltd |  | Camille Dupont | Lucas Ferreira | Brightwave Tech Ltd-GCP-ANF-Database | 0 | 2024-07-11 | 2025-08-19 | 1 | 1 | Launch | Database | iSCSI | ANF | 600 | High | 163 | 362 | Not Started | 2024-10-12 | Follow up with Brightwave Tech Ltd on Database deployment. | Procurement delay |  | USD | 81746.13 | GCP | 9168025 | Complete | CVP Created | 1 | GCPNAGP-GC-006 | No
NAGP-AZ-017 | Copperton Supplies Ltd | Asia Pacific | Copperton Supplies Ltd | Lighthouse | Fiona Clements | Brett Calloway | Copperton Supplies Ltd-Azure-FSxN-File_Storage | 0 | 2024-03-30 | 2025-06-17 | 1 | 0 | Biz Val | File Storage | Windows SQL | FSxN | 450 | High | 59 | 522 |  | 2025-05-28 | Follow up with Copperton Supplies Ltd on File Storage deployment. | Procurement delay |  | USD | 20794.35 | Azure | 1840322 | #N/A | CVP Created | 1 | AzureNAGP-AZ-017 | No
NAGP-GC-009 | Apex Delivery Networks | EMEA-LATAM | Apex Delivery Networks | Searchlight | Camille Dupont | Lucas Ferreira | Apex Delivery Networks-GCP-FSxN-Analytics | 0 | 2024-01-23 | 2025-01-03 | 1 | 0 | Launch | Analytics | SMB | FSxN | 600 | High | 369 | 389 |  | 2024-08-31 | Follow up with Apex Delivery Networks on Analytics deployment. |  |  | USD | 33787.5 | GCP | 4649647 | #N/A | CVP Created | 1 | GCPNAGP-GC-009 | No
NAGP-GC-015 | Dawnridge IoT | Asia Pacific | Dawnridge IoT | Searchlight | Ivan Sokolov | Lucas Ferreira | Dawnridge IoT-GCP-FSxN-Database | 0 | 2024-07-01 | 2024-11-12 | 1 | 0 | Closed Won | Database | NFSv4 | FSxN | 450 | High | 197 | 396 | Not Started | 2024-10-15 | Follow up with Dawnridge IoT on Database deployment. |  |  | USD | 24107.98 | GCP | 4224735 | Future | CVP Created | 1 | GCPNAGP-GC-015 | No
NAGP-AW-005 | Crestline Energy Inc | North America | Crestline Energy Inc | Keystone | Owen Griffith | Chris Dolan | Crestline Energy Inc-AWS-ANF-VMware | 0 | 2024-04-27 | 2025-02-14 | 0 | 1 | Closed Won | VMware | iSCSI | ANF | 500 | High | 181 | 681 | In Progress | 2025-01-14 | Follow up with Crestline Energy Inc on VMware deployment. | Budget freeze |  | USD | 254708.81 | AWS | 5929406 | #N/A | CVP Created | 1 | AWSNAGP-AW-005 | No
NAGP-AW-016 | TerraFin Services | EMEA-LATAM | TerraFin Services | Searchlight | Megan Holt | Ryan Mitchell | TerraFin Services-AWS-FSxN-VMware | 0 | 2024-05-04 | 2025-07-06 | 1 | 1 | Biz Val | VMware | NFSv4 | FSxN | 200 | Medium | 174 | 511 |  | 2025-01-27 | Follow up with TerraFin Services on VMware deployment. | Procurement delay |  | USD | 178212.98 | AWS | 4098370 | #N/A | CVP Created | 1 | AWSNAGP-AW-016 | No
NAGP-GC-005 | Sunridge Gaming Corp | Asia Pacific | Sunridge Gaming Corp | Lighthouse | Anaya Roy | Tara Simmons | Sunridge Gaming Corp-GCP-FSxN-File_Storage | 0 | 2024-05-20 | 2025-04-09 | 0 | 1 | Closed Won | File Storage | NFSv3 | FSxN | 1000 | High | 10 | 118 | In Progress | 2024-10-27 | Follow up with Sunridge Gaming Corp on File Storage deployment. |  |  | USD | 130478.79 | GCP | 3595777 | #N/A | CVP Created | 1 | GCPNAGP-GC-005 | No
NAGP-AZ-009 | Canyon Insurance Ltd | North America | Canyon Insurance Ltd |  | Fiona Clements | Brett Calloway | Canyon Insurance Ltd-Azure-FSxN-Backup_&_Recovery | 0 | 2024-02-15 | 2025-08-12 | 1 | 0 | Production | Backup & Recovery | Windows SQL | FSxN | 1000 | High | 353 | 111 |  | 2024-10-15 | Follow up with Canyon Insurance Ltd on Backup & Recovery deployment. |  |  | USD | 263734.85 | Azure | 7442261 | Started | CVP not Created | 1 | AzureNAGP-AZ-009 | No
NAGP-GC-008 | Polar Fashion Group | EMEA-LATAM | Polar Fashion Group | Searchlight | Rachel Torres | Clay Burgess | Polar Fashion Group-GCP-FSxN-File_Storage | 0 | 2024-02-28 | 2024-11-26 | 0 | 1 | Launch | File Storage | NFSv3 | FSxN | 200 | Medium | 456 | 651 | In Progress | 2025-02-22 | Follow up with Polar Fashion Group on File Storage deployment. | Security review |  | USD | 214577.18 | GCP | 7616612 | Future | CVP Created | 1 | GCPNAGP-GC-008 | No

## 3P
Geo | NAGP ID | NAGP Name | DP ID | DP Name | Account Name | Strategic Programs | Opportunity Owner | Opportunity Owner: Manager | Opportunity Name | Sales Play | Channel | Purchase Type | Stage | Created Date | Close Date | Product Name | Expected Capacity in Terabytes | Ex Capacity Bucket | Days in Sales Stage | Opportunity Age | POC Status | POC Comments | Last Modified Date | Next Step | Blocker Notes | Revenue (converted) Currency | Revenue (converted) | Opportunity Number | Hyperscaler | L2C Status | Comments | Oppty Unique Count | Concat | Top 5
Asia Pacific | NAGP-AW-007 | Pacific Wealth Management | DP-AW-87000 | Pacific Wealth Manag_Partner | Pacific Wealth Management | Searchlight | Aaron Blake | Ryan Mitchell | Pacific Wealth Management-Opp-3317766-AWS-CVO | SAP on Cloud | Indirect | PayGo- Private Offer | Closed Won | 2024-04-15 | 2025-08-12 | CVO | 500 | High | 210 | 187 | Complete |  | 2024-08-05 | Coordinate with partner on Pacific Wealth Management plan. | Contract negotiation | USD | 56818.92 | 3317766 | AWS | #N/A | CVP Created | 1 | AWSNAGP-AW-007 | No
Asia Pacific | NAGP-AW-006 | BlueStar Banking Grp | DP-AW-49601 | BlueStar Banking Grp_Partner | BlueStar Banking Grp | Searchlight | Jessica Lane | Chris Dolan | BlueStar Banking Grp-Opp-4181994-AWS-CVO | Database Modernization | Direct | PayGo- Private Offer | Closed Won | 2024-07-24 | 2025-03-18 | CVO | 100 | Medium | 292 | 406 | In Progress |  | 2025-01-15 | Coordinate with partner on BlueStar Banking Grp plan. | Contract negotiation | USD | 318526.19 | 4181994 | AWS | Complete | CVP Created | 1 | AWSNAGP-AW-006 | No
EMEA-LATAM | NAGP-GC-013 | Lumen Cloud Corp | DP-GC-19257 | Lumen Cloud Corp_Partner | Lumen Cloud Corp | Lighthouse | Rachel Torres | Clay Burgess | Lumen Cloud Corp-Opp-3572001-GCP-Cloud Volumes ONTAP | Data Analytics | Direct | Marketplace | Closed Won | 2024-04-19 | 2025-02-22 | Cloud Volumes ONTAP - Hyperscaler | 200 | Medium | 291 | 151 | Not Started |  | 2024-12-26 | Coordinate with partner on Lumen Cloud Corp plan. | Partner resourcing | USD | 376403.91 | 3572001 | GCP | Future | CVP Created | 1 | GCPNAGP-GC-013 | No
North America | NAGP-AZ-008 | Lakeside Financial Grp | DP-Az-13505 | Lakeside Financial G_Partner | Lakeside Financial Grp |  | Anya Petrov | James Whitfield | Lakeside Financial Grp-Opp-3161891-Azure-Cloud Volumes ONTAP | Database Modernization | Indirect | Private Offer | Production | 2024-06-06 | 2024-12-09 | Cloud Volumes ONTAP - Hyperscaler | 300 | Medium | 209 | 146 | In Progress |  | 2025-03-02 | Coordinate with partner on Lakeside Financial Grp plan. |  | USD | 160692.38 | 3161891 | Azure | Future | CVP Created | 1 | AzureNAGP-AZ-008 | No
Asia Pacific | NAGP-GC-007 | Cosmo Ride Platforms | DP-GC-10765 | Cosmo Ride Platforms_Partner | Cosmo Ride Platforms | Lighthouse | Camille Dupont | Lucas Ferreira | Cosmo Ride Platforms-Opp-9690267-GCP-CVO | VMware Migration | Indirect | BYOL | Biz Val | 2024-06-09 | 2024-11-08 | CVO | 300 | Medium | 211 | 359 |  |  | 2024-12-04 | Coordinate with partner on Cosmo Ride Platforms plan. | Contract negotiation | USD | 455056.53 | 9690267 | GCP | #N/A | CVP Created | 1 | GCPNAGP-GC-007 | No
EMEA-LATAM | NAGP-AZ-003 | Cobalt Telecom Ltd | DP-Az-24953 | Cobalt Telecom Ltd_Partner | Cobalt Telecom Ltd | Searchlight | Yuki Tanaka | James Whitfield | Cobalt Telecom Ltd-Opp-9468390-Azure-Cloud Volumes ONTAP | Cloud & Dev Ops | Direct | PayGo- Private Offer | Production | 2024-05-28 | 2025-02-25 | Cloud Volumes ONTAP - Hyperscaler | 800 | High | 115 | 178 |  |  | 2024-11-16 | Coordinate with partner on Cobalt Telecom Ltd plan. |  | USD | 239127.64 | 9468390 | Azure | Started | CVP Created | 1 | AzureNAGP-AZ-003 | No
North America | NAGP-GC-012 | Ironveil Cybersecurity | DP-GC-41949 | Ironveil Cybersecuri_Partner | Ironveil Cybersecurity |  | Rachel Torres | Clay Burgess | Ironveil Cybersecurity-Opp-4076847-GCP-Cloud Volumes Servic | VMware Migration | Direct | BYOL | Biz Val | 2024-05-03 | 2024-11-08 | Cloud Volumes Service | 500 | High | 87 | 478 | Complete |  | 2024-11-06 | Coordinate with partner on Ironveil Cybersecurity plan. |  | USD | 350800.71 | 4076847 | GCP | Future | CVP Created | 1 | GCPNAGP-GC-012 | No
Asia Pacific | NAGP-GC-005 | Sunridge Gaming Corp | DP-GC-94446 | Sunridge Gaming Corp_Partner | Sunridge Gaming Corp | Lighthouse | Ivan Sokolov | Lucas Ferreira | Sunridge Gaming Corp-Opp-5291399-GCP-Cloud Volumes Servic | Database Modernization | Indirect | Private Offer | Closed Won | 2024-02-08 | 2025-07-17 | Cloud Volumes Service | 800 | High | 52 | 285 | Complete |  | 2024-12-03 | Coordinate with partner on Sunridge Gaming Corp plan. | Contract negotiation | USD | 243105.22 | 5291399 | GCP | Future | CVP Created | 1 | GCPNAGP-GC-005 | No
North America | NAGP-AZ-013 | Horizon Auto Group | DP-Az-56704 | Horizon Auto Group_Partner | Horizon Auto Group |  | Dean Forsyth | Sophie Harrington | Horizon Auto Group-Opp-9996784-Azure-Cloud Volumes ONTAP | Cloud & Dev Ops | Indirect | BYOL | Production | 2024-05-06 | 2024-10-26 | Cloud Volumes ONTAP - Hyperscaler | 200 | Medium | 175 | 61 |  |  | 2025-02-10 | Coordinate with partner on Horizon Auto Group plan. | Partner resourcing | USD | 184223.61 | 9996784 | Azure | Future | CVP Created | 1 | AzureNAGP-AZ-013 | No
EMEA-LATAM | NAGP-AZ-010 | Silverline Media Corp | DP-Az-27393 | Silverline Media Cor_Partner | Silverline Media Corp | Lighthouse | Yuki Tanaka | James Whitfield | Silverline Media Corp-Opp-8380771-Azure-Cloud Volumes ONTAP | Cloud & Dev Ops | Indirect | Marketplace | Biz Val | 2024-05-01 | 2025-04-05 | Cloud Volumes ONTAP - Hyperscaler | 300 | Medium | 173 | 363 | Not Started |  | 2024-09-27 | Coordinate with partner on Silverline Media Corp plan. |  | USD | 184958.17 | 8380771 | Azure | Started | CVP Created | 1 | AzureNAGP-AZ-010 | No
EMEA-LATAM | NAGP-AW-010 | Atlas Capital Partners | DP-AW-88617 | Atlas Capital Partne_Partner | Atlas Capital Partners |  | Derek Santos | Ryan Mitchell | Atlas Capital Partners-Opp-5067471-AWS-Cloud Volumes Servic | Data Analytics | Direct | Private Offer | Biz Val | 2024-03-16 | 2024-09-27 | Cloud Volumes Service | 300 | Medium | 107 | 204 | Not Started |  | 2024-08-23 | Coordinate with partner on Atlas Capital Partners plan. |  | USD | 45654.47 | 5067471 | AWS | #N/A | CVP Created | 1 | AWSNAGP-AW-010 | No
Asia Pacific | NAGP-AZ-005 | Pacifica Utilities Corp | DP-Az-12184 | Pacifica Utilities C_Partner | Pacifica Utilities Corp |  | Dean Forsyth | Sophie Harrington | Pacifica Utilities Corp-Opp-8449437-Azure-Cloud Volumes ONTAP | SAP on Cloud | Indirect | Marketplace | Production | 2024-05-08 | 2025-07-12 | Cloud Volumes ONTAP - Hyperscaler | 800 | High | 31 | 439 |  |  | 2025-05-29 | Coordinate with partner on Pacifica Utilities Corp plan. | Partner resourcing | USD | 120709.07 | 8449437 | Azure | Future | CVP Created | 1 | AzureNAGP-AZ-005 | No

## Top 5
Hyperscaler | NAGP ID | NAGP Name | Product Offering
AWS | NAGP-AW-014 | Redwood Genomics | 3P
AWS | NAGP-AW-011 | Ironbridge Manufacturing | 3P
AWS | NAGP-AW-001 | Pinnacle Financial Corp | 3P
AWS | NAGP-AW-003 | Orion Retail Group | 3P
AWS | NAGP-AW-013 | Northgate Pharma | 1P
Azure | NAGP-AZ-007 | NovaTech Platforms Inc | 3P
Azure | NAGP-AZ-014 | Celestia Biotech | 3P
Azure | NAGP-AZ-011 | Ridgeway Pharma Group | 3P
Azure | NAGP-AZ-008 | Lakeside Financial Grp | 1P
Azure | NAGP-AZ-002 | Emerald Property Group | 3P
GCP | NAGP-GC-012 | Ironveil Cybersecurity | 1P
GCP | NAGP-GC-016 | Vortex Mobility Inc | 1P
GCP | NAGP-GC-003 | Helix Streaming Ltd | 3P
GCP | NAGP-GC-017 | Alpine Data Ventures | 1P
GCP | NAGP-GC-001 | Stratus Digital Media | 3P

## CS MANAGER REPO
Hyperscaler | CSM/CSE | CS Manager Name | Geo
AWS | Aaron Blake | Ryan Mitchell | AMER
AWS | Megan Holt | Ryan Mitchell | AMER
AWS | Derek Santos | Ryan Mitchell | AMER
AWS | Priya Kapoor | Nick Jordan | AMER
AWS | Tyler Reeves | Nick Jordan | AMER
AWS | Sandra Park | Nick Jordan | AMER
AWS | Marcus Webb | Chris Dolan | AMER
AWS | Jessica Lane | Chris Dolan | AMER
AWS | Owen Griffith | Chris Dolan | AMER
Azure | Isabelle Morel | Sophie Harrington | EMEA
Azure | Dean Forsyth | Sophie Harrington | EMEA
Azure | Chloe Ramsay | Sophie Harrington | EMEA
Azure | Nathan Kowalski | Brett Calloway | AMER
Azure | Fiona Clements | Brett Calloway | AMER
Azure | Raj Mehta | Brett Calloway | AMER
Azure | Yuki Tanaka | James Whitfield | APAC
Azure | Tom Gallagher | James Whitfield | APAC
Azure | Anya Petrov | James Whitfield | APAC
GCP | Rachel Torres | Clay Burgess | AMER
GCP | Sam Cheng | Clay Burgess | AMER
GCP | Jake Morrison | Clay Burgess | AMER
GCP | Kenji Watanabe | Tara Simmons | APAC
GCP | Anaya Roy | Tara Simmons | APAC
GCP | Liam O'Brien | Tara Simmons | APAC
GCP | Eva Richter | Lucas Ferreira | EMEA
GCP | Ivan Sokolov | Lucas Ferreira | EMEA
GCP | Camille Dupont | Lucas Ferreira | EMEA